## Risks Classification
Probability | Very High | MEDIUM | MEDIUM | HIGH | HIGH | HIGH
| High | MEDIUM | MEDIUM | MEDIUM | HIGH | HIGH
| Moderate | LOW | MEDIUM | MEDIUM | MEDIUM | HIGH
| Few | LOW | LOW | MEDIUM | MEDIUM | MEDIUM
| Unlikely | LOW | LOW | LOW | MEDIUM | MEDIUM
|  | None | Very Minor | Moderate | High | Very high
SEVERITY

## FMEA
Potential Failure Mode and Effects Analysis (FMEA)
Potential Failure Mode(s) | Sev | Prob | Risk Priority Number | Recommended Actions | Responsibility & Target Completion Date | Actions Taken
Unable to work with RENESAS Board outside of UTEQ | 5 | 5 | 25 | Buy a RENESAS board to work outside UTEQ | Closed - 10/31/2019 | Work on UTEQ on weekdays from 20:00 to 22:00
Unaccurate planning due to lack of knowledge on project's complexity | 3 | 5 | 15 | Contact tutor from the Embedded Software Course to send questions | Closed - 10/25/2019 | Meeting minutes with tutor
Uncalibrated Sensors | 3 | 2 | 6 | Test each sensor before the integration | Open - | Effect-Hall sensor needs to be modified from an interruption to an input capture event
Unstable controller | 4 | 4 | 8 | Evaluate changing of controller type | Open - | Controller needs to be updated
Damaged Components | 4 | 2 | 8 | Keep documents with generic components name in case is needed to switch to another | Closed - 10/04/2019 | All components such as PWM, H-Bridge, Hall-effect sensor were tested and no damage was present.
Change in requirements | 3 | 2 | 6 | Show SWRA at the beginning of the project to the client and keep weekly meetings to review changes | Closed - 10/11/2019 | Weekly meetings with costumer were held and SWRA was approved.
Team member's unavailability to work on project outside of Fridays or Saturdays | 4 | 5 | 20 | Keep planning smart to avoid working overtime | Closed - 10/30/2019 | Development Team worked on weekends from 10/21/2019 to 10/30/2019 to complete the assignments.