## Project Plan
SMC Integration Project Plan
[5 empty] | Highlight Period | 1 |  |  | Plan Duration | [6 empty] | Real Start |  |  |  |  | % Completed | [5 empty] | Real (out of plan) | [7 empty] | % Completed (out of plan)
ACTIVITY | INITIAL FISCAL WEEK ON PLAN | PLANNED FISCAL WEEK DURATION | REAL START FISCAL WEEK ON PLAN | ACTUAL PERIOD DURATION | PERCENTAJE COMPLETED | FISCAL WEEK
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Software Requirements Document | 36 | 1 | 38 | 1 | 100%
Add Project Scope on SDP | 37 | 1 | 38 | 1 | 100%
Add Development Methodologies on SDP | 38 | 1 | 38 | 1 | 100%
Add Non-functional Requirements on SWRA | 38 | 1 | 38 | 1 | 100%
Add Functional requirements on SWRA | 42 | 1 | 38 | 1 | 100%
Software Development Plan Document | 42 | 1 | 38 | 1 | 100%
Configure LCD | 42 | 1 | 39 | 1 | 100%
Add Planning Description on SDP | 42 | 1 | 39 | 1 | 100%
Add Software Standards and Naming Conventions on SDP | 40 | 1 | 39 | 1 | 100%
Add Project Estimates on SDP | 40 | 1 | 39 | 1 | 100%
Add Problem Solving Strategy on SDP | 41 | 1 | 39 | 1 | 100%
Configure PWM | 39 | 1 | 40 | 1 | 100%
Configure ADC | 39 | 1 | 40 | 1 | 100%
Add Deliverables Description | 39 | 1 | 40 | 1 | 100%
Add Design Description on SDD | 39 | 1 | 40 | 1 | 100%
Configure Hall-effect sensor | 39 | 1 | 41 | 1 | 100%
Add Release Description | 39 | 1 | 41 | 1 | 100%
Select and Design Control Algorithm | 39 | 1 | 42 | 1 | 100%
Develop Control Algorithm | 39 | 1 | 42 | 1 | 100%
Short to Battery Enhancement | 39 | 1 | 42 | 1 | 100%
Short to Ground Enhancement | 39 | 1 | 42 | 1 | 100%
Add FMEA Document | 39 | 1 | 42 | 1 | 100%
Add Testing Description on SDP | 40 | 1 | 43 | 1 | 100%
Add Meeting Minutes | 40 | 1 | 43 | 1 | 100%
Add Software and Systems Diagram on SDD | 40 | 1 | 43 | 1 | 100%
Add Results and Lessons Learned on SDP | 40 | 1 | 43 | 1 | 100%
BlackBox Tests and Results | 40 | 1 | 44 | 1 | 100%
WhiteBox Tests and Results | 40 | 1 | 44 | 1 | 100%
Integration Tests and Results | 40 | 1 | 44 | 1 | 100%