## Project Plan
SMC Integration Project Plan
[5 empty] | Highlight Period | 1 |  |  | Plan Duration | [6 empty] | Real Start |  |  |  |  | % Completed | [5 empty] | Real (out of plan) | [7 empty] | % Completed (out of plan)
ACTIVITY | INITIAL FISCAL WEEK ON PLAN | PLANNED FISCAL WEEK DURATION | REAL START FISCAL WEEK ON PLAN | ACTUAL PERIOD DURATION | PERCENTAJE COMPLETED | FISCAL WEEK
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
SWRA Document | 36 | 2 | 37 | 3 | 0%
Software Design Document | 37 | 2 | 37 | 2 | 0%
Software Standards Document | 38 | 1 | 39 | 2 | 0%
Naming Conventions Document | 38 | 1 | 39 | 2 | 0%
Blackbox Test Baseline | 42 | 1 |  |  | 0%
Whitebox Test Baseline | 42 | 1 |  |  | 0%
CCR Baseline | 41 | 1 |  |  | 0%
Integration Testing Baseline | 42 | 1 |  |  | 0%
Validation Testing Baseline | 42 | 1 |  |  | 0%
Throughput RAM Flash Procedure | 40 | 1 | 41 | 1 | 0%
Quality Audit | 40 | 1 | 41 | 1 | 0%
Control Algorithm Design | 41 | 1 | 42 |  | 0%
Initial Configuration | 39 | 1 | 40 | 1 | 0%
• EEPROM Memory | 39 | 1 | 40 | 1 | 0%
• Interruption Timer | 39 | 1 | 40 | 1 | 0%
• Analogic Digital Converter | 39 | 1 | 40 | 1 | 0%
• Pulse Width Modulation | 39 | 1 | 40 | 1 | 0%
• Digital Input / Output | 39 | 1 | 40 | 1 | 0%
• WatchDog Timer | 39 | 1 | 40 | 1 | 0%
• Input Capture | 39 | 1 | 40 | 1 | 0%
• LCD Display | 39 | 1 | 40 | 1 | 0%
• SPI Port | 39 | 1 | 40 | 1 | 0%
Scheduler Design | 39 | 1 | 40 | 1 | 0%
Scheduler Implementation | 40 | 1 | 41 | 1 | 0%